## Raw Data
Work Item Type | ID | Title | State | Iteration Path | Resolved Date | Story Points | Activated Date | Created Date | PICategory
User Story | 485934 | Configure the Casting Model in MES | Resolved | DSM-Firmenich\Sprint 01 | 2025-04-09 10:47 | 2 | 2025-04-08 14:11 | 2025-03-20 09:49 | Modelling & Configuration
User Story | 485932 | Configure the Final Packaging Model in MES | Resolved | DSM-Firmenich\Sprint 01 | 2025-04-09 10:48 | 1 | 2025-04-08 14:11 | 2025-03-20 09:47 | Modelling & Configuration
User Story | 485927 | Master Data Configuration for Pouching in MES | Resolved | DSM-Firmenich\Sprint 01 | 2025-04-09 10:49 | 1 | 2025-04-08 14:11 | 2025-03-20 09:37 | Modelling & Configuration
User Story | 485930 | Configure Site Model for HA-CMC Powder & Raw Material Weighing | Resolved | DSM-Firmenich\Sprint 01 | 2025-04-09 13:00 | 1 | 2025-04-09 10:48 | 2025-03-20 09:43 | Modelling & Configuration
User Story | 485924 | Execute the Weighing Process - IoT W&D | Resolved | DSM-Firmenich\Sprint 01 | 2025-04-09 16:11 | 8 | 2025-03-27 14:04 | 2025-03-20 09:27 | Integration - Equipment / Connect IoT
User Story | 485917 | Configure Products for Weighing Process | Resolved | DSM-Firmenich\Sprint 01 | 2025-04-09 18:03 | 2 | 2025-03-27 10:54 | 2025-03-20 08:53 | Modelling & Configuration
Bug | 524271 | Source Step configuration by Product (Consumable) not available | Resolved | DSM-Firmenich\Sprint 01 | 2025-08-22 17:39 | 3 | 2025-08-18 10:20 | 2025-08-14 09:40 | Integration - 3rd Party
User Story | 485914 | Trigger PO Push from SAP to MES | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-15 14:44 | 5 | 2025-04-15 14:43 | 2025-03-20 08:35 | Integration - 3rd Party
User Story | 485915 | Push Raw Material Data from SAP to MES | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-15 14:44 | 5 | 2025-04-10 09:33 | 2025-03-20 08:41 | Integration - 3rd Party
User Story | 485919 | Process Material Creation & Assign Target Quantity | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-17 09:24 | 5 | 2025-04-08 09:13 | 2025-03-20 09:06 | Customization - Business Logic
User Story | 486236 | Post Weighing actions - After W&D | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-18 10:17 | 2 | 2025-04-14 17:48 | 2025-03-21 11:34 | Customization - Business Logic
Bug | 494699 | [Bug] - 491180 - AC1 -HA-CMC PO release and material creation | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-22 15:23 | 1 | 2025-04-22 10:07 | 2025-04-21 23:00 | Customization - Business Logic
Bug | 494648 | [Bug] - 485920 - AC4 - Display and Use the "Create Materials for W&D" Button & Wizard | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-22 22:09 | 1 | 2025-04-22 10:29 | 2025-04-21 18:00 | Customization - GUI Logic
Bug | 494646 | [Bug] - 485920 - AC3- Display and Use the "Create Materials for W&D" Button & Wizard | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-22 22:10 | 1 | 2025-04-22 09:44 | 2025-04-21 17:52 | Customization - GUI Logic
Bug | 494900 | [Bug] - 485920 - AC1- Button to Create Material is visible | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-22 22:10 | 1 | 2025-04-22 22:07 | 2025-04-22 12:51 | Customization - GUI Logic
Bug | 494982 | [Bug] - PO Details Page & Material Details Page Issues | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-23 10:07 | 1 | 2025-04-23 10:07 | 2025-04-22 16:22 | Customization - GUI Logic
User Story | 495045 | Import Production Order - Delivery Tolerance fields change | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-23 11:24 | 2 | 2025-04-22 21:18 | 2025-04-22 21:16 | Integration - 3rd Party
User Story | 491180 | HA-CMC PO release and material creation | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-23 11:26 | 5 | 2025-04-16 09:13 | 2025-04-08 11:17 | Customization - Business Logic
Bug | 494670 | [Bug] - 485920 - AC9 - Display and Use the "Create Materials for W&D" Button & Wizard | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-23 14:04 | 1 | 2025-04-22 10:29 | 2025-04-21 18:31 | Customization - Business Logic
User Story | 491215 | HA-CMC Operator cockpit design and implementation | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-23 14:04 | 8 | 2025-04-17 09:24 | 2025-04-08 11:42 | Customization - GUI Logic
User Story | 492332 | Create Documentation for W&D configuration | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-23 14:47 | 1 | 2025-04-23 10:33 | 2025-04-10 17:36 | Modelling & Configuration
User Story | 491490 | Configuring OK/NOK Checklist | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-23 17:14 | 1 | 2025-04-11 16:32 | 2025-04-08 18:04 | Modelling & Configuration
User Story | 491485 | Interlock Framework | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-23 17:52 | 5 | 2025-04-14 14:03 | 2025-04-08 17:58 | Customization - Business Logic
User Story | 491491 | Data Collection Framework | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-23 17:52 | 8 | 2025-04-16 14:02 | 2025-04-08 18:05 | Customization - Business Logic
User Story | 492690 | Feature Validation - HA-CMC PO release and material creation | Resolved | DSM-Firmenich\Sprint 02 | 2025-04-24 15:51 | 0 | 2025-04-23 19:07 | 2025-04-11 14:10 | Customization - Business Logic
User Story | 492271 | Feature Validation - HA-CMC Operator cockpit design and implementation | Resolved | DSM-Firmenich\Sprint 02 | 2025-07-07 09:49 | 0 | 2025-07-07 09:49 | 2025-04-10 15:50 | Customization - Business Logic
Bug | 496565 | Casting Documentation Error | Resolved | DSM-Firmenich\Sprint 03 | 2025-04-29 12:10 | 1 | 2025-04-29 12:10 | 2025-04-29 12:01 | Modelling & Configuration
Bug | 496389 | Service is Incorrect in Master Data | Resolved | DSM-Firmenich\Sprint 03 | 2025-04-30 14:04 | 1 | 2025-04-30 14:04 | 2025-04-28 11:21 | Modelling & Configuration
User Story | 485937 | Allow EDC Quantity Adjustments for Losses or Bonuses and track time constraints | Resolved | DSM-Firmenich\Sprint 03 | 2025-04-30 14:07 | 2 | 2025-04-22 21:30 | 2025-03-20 09:56 | Customization - Business Logic
User Story | 497030 | [ENHANCEMENT] Update Base Model | Resolved | DSM-Firmenich\Sprint 03 | 2025-04-30 18:03 | 1 | 2025-04-30 17:59 | 2025-04-30 17:23 | Modelling & Configuration
User Story | 495910 | Bug Validation - HA-CMC PO release and material creation | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-02 12:14 | 0 | 2025-05-02 12:14 | 2025-04-24 15:33 | Customization - Business Logic
Bug | 495809 | Batch is not inherited to the Material | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-02 12:14 | 1 | 2025-04-25 12:13 | 2025-04-24 14:29 | Customization - Business Logic
Bug | 497237 | Wrong Area in Documentation | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-02 12:29 | 1 | 2025-05-02 12:00 | 2025-05-02 11:46 | Modelling & Configuration
User Story | 495245 | Configure Interlock for EDC Reaction | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-02 14:03 | 2 | 2025-04-29 14:03 | 2025-04-23 11:45 | Integration - Equipment / Connect IoT
Bug | 495483 | Problems identified during the Demo | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-02 14:10 | 1 | 2025-04-29 14:37 | 2025-04-23 19:02 | Customization - GUI Logic
User Story | 495260 | Configure Interlock for Precipitation | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-02 14:12 | 2 | 2025-05-02 14:12 | 2025-04-23 11:55 | Integration - Equipment / Connect IoT
User Story | 492318 | Collect Weight with a DataCollection - Manual Input | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-02 15:29 | 1 | 2025-04-29 14:47 | 2025-04-10 16:48 | Modelling & Configuration
Bug | 497302 | Naming is wrong on the Documentation | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-02 17:45 | 1 | 2025-05-02 17:45 | 2025-05-02 17:19 | Modelling & Configuration
User Story | 495246 | Configure Collection of Data for EDC Reaction | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-03 15:17 | 2 | 2025-04-30 09:58 | 2025-04-23 11:47 | Integration - Equipment / Connect IoT
User Story | 495258 | Configure Collection of Data for Precipitation | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-03 15:17 | 2 | 2025-05-03 15:17 | 2025-04-23 11:54 | Integration - Equipment / Connect IoT
User Story | 495244 | Pre preparation checklist at Track-In for EDC Reaction | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-05 16:40 | 1 | 2025-05-05 16:40 | 2025-04-23 11:44 | Modelling & Configuration
User Story | 495262 | Configure Checklist at Track-In for Filter + Dryer + Milling | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-05 16:40 | 1 | 2025-05-05 16:40 | 2025-04-23 11:57 | Modelling & Configuration
User Story | 495264 | Configure Interlock for Filter+Dryer+Milling | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-05 16:53 | 2 | 2025-05-03 15:17 | 2025-04-23 11:58 | Integration - Equipment / Connect IoT
User Story | 495263 | Configure Collection of Data for Filter+Dryer+Milling | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-05 16:53 | 2 | 2025-05-03 15:17 | 2025-04-23 11:57 | Integration - Equipment / Connect IoT
User Story | 496535 | [Enhancement] Dissolution Driver | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-05 17:03 | 1 | 2025-05-05 16:53 | 2025-04-29 11:02 | Integration - Equipment / Connect IoT
User Story | 495248 | Combine Operation for EDC Reaction (Full Process Test) | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-06 07:37 | 3 | 2025-05-02 09:58 | 2025-04-23 11:51 | Customization - Business Logic
User Story | 495271 | Allow Partial Trackout and configure Loss Reasons | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-06 14:05 | 1 | 2025-05-05 15:13 | 2025-04-23 12:01 | Modelling & Configuration
User Story | 495927 | Feature Validation - HA-CMC Weighing process Implementation | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-06 18:24 | 0 | 2025-05-06 13:13 | 2025-04-24 15:46 | Customization - Business Logic
User Story | 495315 | Create Product for Castsheets | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-07 14:09 | 1 | 2025-04-30 11:13 | 2025-04-23 12:49 | Modelling & Configuration
Bug | 495481 | Raw Material Weighing - Multiple ACs to be fixed | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-07 14:10 | 1 | 2025-05-05 19:43 | 2025-04-23 18:58 | Customization - GUI Logic
User Story | 496378 | Bug Validation - HA-CMC Operator cockpit design and implementation | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-08 09:39 | 0 | 2025-05-05 09:20 | 2025-04-28 10:35 | Customization - Business Logic
User Story | 485920 | Display and Use the "Create Materials for W&D" Button & Wizard | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-08 11:45 | 8 | 2025-04-24 15:30 | 2025-03-20 09:09 | Customization - GUI Logic
User Story | 495995 | Customer Support | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-08 11:47 | 0 | 2025-05-08 11:47 | 2025-04-24 17:44 | Customer Support
User Story | 498781 | [Connect IoT] Automatic Tests enhancement | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-09 15:02 | 0 | 2025-05-08 13:32 | 2025-05-08 13:32 | Release Management
User Story | 492267 | Feature Validation - Pre-preparation of consumables | Resolved | DSM-Firmenich\Sprint 03 | 2025-05-12 11:16 | 0 | 2025-05-02 15:59 | 2025-04-10 15:49 | Integration - 3rd Party
User Story | 495948 | Backlog Refinement & Preparation | Resolved | DSM-Firmenich\Sprint 03 | 2025-07-13 20:18 | 0 | 2025-07-13 20:18 | 2025-04-24 16:24 | Modelling & Configuration
Bug | 498634 | Missing Filters on the wizard fields | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-08 16:12 | 2 | 2025-05-08 09:55 | 2025-05-08 09:46 | Customization - GUI Logic
Bug | 498860 | W&D Button does not appear | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-08 16:12 | 1 | 2025-05-08 15:09 | 2025-05-08 15:09 | Customization - GUI Logic
User Story | 498887 | Configure Feeders for HCL | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-09 11:19 | 1 | 2025-05-09 11:19 | 2025-05-08 16:55 | Modelling & Configuration
Bug | 497072 | Import PO fails because Boolean is considered null | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-09 11:26 | 1 | 2025-05-08 15:53 | 2025-04-30 18:42 | Integration - 3rd Party
User Story | 496824 | Add Button "Manage -> Consumables" to the Operator Cockpit | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-09 14:55 | 1 | 2025-05-08 16:38 | 2025-04-30 12:09 | Customization - GUI Logic
User Story | 496834 | Create Checklist on Track-In | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-12 17:12 | 1 | 2025-05-09 14:17 | 2025-04-30 12:31 | Modelling & Configuration
Bug | 499357 | Unable to reprocess Integration Entries | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-14 08:56 | 1 | 2025-05-13 12:23 | 2025-05-12 19:36 | Integration - ERP
User Story | 496815 | Configure Interlock for Resuspension | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-14 09:00 | 2 | 2025-05-09 11:40 | 2025-04-30 11:59 | Integration - Equipment / Connect IoT
Bug | 499733 | Name Generator + Weighing PO release | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-14 13:46 | 1 | 2025-05-14 10:13 | 2025-05-14 09:41 | Customization - Business Logic
User Story | 496831 | Configure Interlock for Holding | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-14 14:17 | 2 | 2025-05-14 10:21 | 2025-04-30 12:18 | Integration - Equipment / Connect IoT
User Story | 496843 | Ensure Resource can hold different products at once | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-14 17:14 | 1 | 2025-05-09 14:13 | 2025-04-30 12:49 | Modelling & Configuration
User Story | 496821 | Configure Collection of Data for Resuspension | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-16 15:22 | 2 | 2025-05-15 09:45 | 2025-04-30 12:01 | Integration - Equipment / Connect IoT
User Story | 496830 | Configure Collection of Data for Holding | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-16 15:26 | 2 | 2025-05-16 08:17 | 2025-04-30 12:16 | Integration - Equipment / Connect IoT
User Story | 495314 | Create Material with Unit Castsheets | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-19 09:32 | 5 | 2025-05-06 07:37 | 2025-04-23 12:39 | Customization - Business Logic
Bug | 500427 | Resuspension DC missing in Default Master Data | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-19 10:43 | 1 | 2025-05-19 10:42 | 2025-05-16 18:20 | Modelling & Configuration
Bug | 500434 | Holding DC MD Not available and DC Instance Not Created | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-19 10:43 | 1 | 2025-05-19 10:42 | 2025-05-16 20:15 | Integration - Equipment / Connect IoT
User Story | 496820 | Read HCL Tag and perform automatic Combine at Track-Out | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-19 11:19 | 5 | 2025-05-09 11:37 | 2025-04-30 12:01 | Integration - Equipment / Connect IoT
User Story | 498658 | Feature Validation - Drying Process Implementation | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-19 14:03 | 0 | 2025-05-16 21:06 | 2025-05-08 10:02 | Customization - Business Logic
Bug | 500429 | Resuspension Material Track out Exception | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-19 14:05 | 1 | 2025-05-19 10:43 | 2025-05-16 18:29 | Customization - Business Logic
User Story | 496835 | Configure Interlock for Casting | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-19 17:19 | 2 | 2025-05-16 18:42 | 2025-04-30 12:31 | Integration - Equipment / Connect IoT
User Story | 496838 | Collect data per Castsheet | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-20 00:09 | 5 | 2025-05-19 09:33 | 2025-04-30 12:41 | Integration - Equipment / Connect IoT
User Story | 495930 | Feature Validation - Casting PO release and material creation | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-21 17:55 | 0 | 2025-05-16 11:28 | 2025-04-24 15:48 | Customization - Business Logic
User Story | 500204 | Correct Ports to 10000 | Resolved | DSM-Firmenich\Sprint 04 | 2025-05-22 14:56 | 0 | 2025-05-15 17:08 | 2025-05-15 17:08 | Integration - Equipment / Connect IoT
User Story | 498635 | Bug Validation - Raw Material Weighing Implementation | Resolved | DSM-Firmenich\Sprint 05 | 2025-05-16 15:44 | 0 | 2025-05-16 15:44 | 2025-05-08 09:47 | Customization - GUI Logic
User Story | 500257 | Configure Interlock for Cutting | Resolved | DSM-Firmenich\Sprint 05 | 2025-05-23 10:22 | 2 | 2025-05-22 14:05 | 2025-05-16 09:13 | Integration - Equipment / Connect IoT
User Story | 500296 | Validate Scale at Track-In | Resolved | DSM-Firmenich\Sprint 05 | 2025-05-23 19:47 | 3 | 2025-05-20 08:36 | 2025-05-16 10:31 | Customization - Business Logic
User Story | 496840 | Record loss at Trackout | Resolved | DSM-Firmenich\Sprint 05 | 2025-05-26 10:37 | 3 | 2025-05-20 18:36 | 2025-04-30 12:45 | Customization - Business Logic
User Story | 500288 | Configure Collection of Data for Cutting | Resolved | DSM-Firmenich\Sprint 05 | 2025-05-26 12:04 | 2 | 2025-05-23 12:25 | 2025-05-16 10:19 | Integration - Equipment / Connect IoT
User Story | 500309 | Create material on PO release | Resolved | DSM-Firmenich\Sprint 05 | 2025-05-28 13:22 | 3 | 2025-05-27 10:16 | 2025-05-16 11:21 | Customization - Business Logic
User Story | 500312 | Configure Collection of Data for Full Pouching | Resolved | DSM-Firmenich\Sprint 05 | 2025-06-03 22:20 | 2 | 2025-06-02 14:03 | 2025-05-16 11:46 | Integration - Equipment / Connect IoT
User Story | 500270 | Implement Cutting Process | Resolved | DSM-Firmenich\Sprint 05 | 2025-06-04 11:26 | 8 | 2025-05-26 12:06 | 2025-05-16 09:40 | Customization - Business Logic
User Story | 505200 | Checklist for Signature | Resolved | DSM-Firmenich\Sprint 05 | 2025-06-04 18:54 | 0 | 2025-06-04 16:25 | 2025-06-03 13:12 | Modelling & Configuration
Bug | 503871 | LOD must not be a mandatory field | Resolved | DSM-Firmenich\Sprint 06 | 2025-06-09 12:24 | 2 | 2025-06-05 09:18 | 2025-05-28 14:41 | Integration - 3rd Party
User Story | 500292 | Integrate Check Weight Scale | Resolved | DSM-Firmenich\Sprint 06 | 2025-06-11 09:50 | 5 | 2025-06-06 10:08 | 2025-05-16 10:25 | Integration - Equipment / Connect IoT
User Story | 502421 | Feature Validation - Pouching PO release and material creation | Resolved | DSM-Firmenich\Sprint 06 | 2025-06-11 10:50 | 0 | 2025-06-04 10:54 | 2025-05-22 19:59 | Customization - Business Logic
User Story | 500310 | Implement Rework Operator Cockpit | Resolved | DSM-Firmenich\Sprint 06 | 2025-06-12 18:15 | 5 | 2025-05-28 07:34 | 2025-05-16 11:21 | Customization - GUI Logic
Bug | 504149 | Operator Cockpit Feature for Role assignation | Resolved | DSM-Firmenich\Sprint 06 | 2025-06-16 21:33 | 1 | 2025-06-16 21:33 | 2025-05-29 13:42 | Customization - Business Logic
Bug | 499501 | Notification is not being created for the Data Collection Framework | Resolved | DSM-Firmenich\Sprint 06 | 2025-06-17 14:43 | 1 | 2025-06-16 10:26 | 2025-05-13 11:54 | Integration - Equipment / Connect IoT
User Story | 505602 | Configure DHT Process Implementation Master Data | Resolved | DSM-Firmenich\Sprint 06 | 2025-06-17 19:18 | 1 | 2025-06-11 20:04 | 2025-06-04 16:52 | Modelling & Configuration
User Story | 505597 | Validate Scale at Track-In | Resolved | DSM-Firmenich\Sprint 06 | 2025-06-17 20:04 | 1 | 2025-06-17 14:04 | 2025-06-04 16:42 | Customization - Business Logic
User Story | 505599 | Configure Collection of Data for Half/Quarter Pouching - Sleeves | Resolved | DSM-Firmenich\Sprint 06 | 2025-06-17 20:04 | 2 | 2025-06-17 14:04 | 2025-06-04 16:48 | Integration - Equipment / Connect IoT
User Story | 505600 | Validate Scale at Track-In | Resolved | DSM-Firmenich\Sprint 06 | 2025-06-17 20:04 | 1 | 2025-06-17 14:04 | 2025-06-04 16:49 | Customization - Business Logic
User Story | 505596 | Configure Collection of Data for Half/Quarter Pouching | Resolved | DSM-Firmenich\Sprint 06 | 2025-06-17 20:04 | 2 | 2025-06-17 14:04 | 2025-06-04 16:41 | Integration - Equipment / Connect IoT
User Story | 499866 | Check-Weight Operator cockpit design and implementation | Resolved | DSM-Firmenich\Sprint 06 | 2025-06-23 14:26 | 8 | 2025-05-23 13:20 | 2025-05-14 16:17 | Customization - GUI Logic
User Story | 500297 | Create Service for "Confirm Weight" | Resolved | DSM-Firmenich\Sprint 06 | 2025-06-24 09:22 | 8 | 2025-06-20 17:11 | 2025-05-16 10:35 | Customization - Business Logic
User Story | 502417 | Feature Validation - Implement Rework Operator Cockpit | Resolved | DSM-Firmenich\Sprint 06 | 2025-07-07 09:47 | 0 | 2025-07-03 18:38 | 2025-05-22 19:49 | Customization - Business Logic
User Story | 505952 | Sprint 06 Tax | Resolved | DSM-Firmenich\Sprint 06 | 2025-07-13 20:19 | 0 | 2025-06-16 15:33 | 2025-06-05 10:42 | Sprint Execution
User Story | 505965 | Backlog Refinement & Preparation | Resolved | DSM-Firmenich\Sprint 06 | 2025-07-13 20:19 | 0 | 2025-07-13 20:19 | 2025-06-05 10:47 | Modelling & Configuration
User Story | 507835 | Create Client MasterData | Resolved | DSM-Firmenich\Sprint 06 | 2025-07-13 20:19 | 0 | 2025-06-16 11:16 | 2025-06-16 11:16 | Modelling & Configuration
User Story | 508033 | Master Data Reconciliation | Resolved | DSM-Firmenich\Sprint 06 | 2025-07-13 20:19 | 0 | 2025-07-13 20:19 | 2025-06-16 18:13 | Modelling & Configuration
User Story | 505367 | Feature Validation - DHT Process Implementation | Resolved | DSM-Firmenich\Sprint 06 | 2025-08-06 14:53 |  | 2025-07-31 09:56 | 2025-06-04 09:15 | Customization - Business Logic
Bug | 509166 | Wrong Kepware Device name on EDC Reaction Driver Tags | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-23 14:01 | 1 | 2025-06-23 13:37 | 2025-06-20 12:52 | Integration - Equipment / Connect IoT
User Story | 494145 | [ENHANCEMENT] Update PO fields and Allow BOM Source Step Configuration | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-25 10:23 | 5 | 2025-06-23 09:39 | 2025-04-17 18:50 | Integration - 3rd Party
Bug | 508845 | Change Good/Bad Parts Tags to SmartTable CustomIoTTagContext | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-25 10:26 | 2 | 2025-06-24 14:25 | 2025-06-18 15:19 | Integration - Equipment / Connect IoT
Bug | 509203 | Remove Casting Track-Out Data Collection | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-25 15:26 | 2 | 2025-06-25 12:23 | 2025-06-20 14:19 | Customization - Business Logic
User Story | 505601 | Call and adapt if needed the Service for "Confirm Weight" | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-26 14:05 | 3 | 2025-06-26 14:03 | 2025-06-04 16:50 | Customization - Business Logic
User Story | 510403 | Feature Validation - Enhancement - Update PO fields and Allow BOM Source Step Configuration | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-26 14:07 | 0 | 2025-06-26 14:06 | 2025-06-25 14:01 | Integration - 3rd Party
User Story | 492274 | Feature Validation - Dissolution process Implementation | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-26 14:09 | 0 | 2025-05-26 14:01 | 2025-04-10 15:51 | Customization - Business Logic
User Story | 495914 | Feature Validation - EDC Reaction process Implementation | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-26 14:09 | 0 | 2025-05-26 17:32 | 2025-04-24 15:37 | Customization - Business Logic
User Story | 495920 | Feature Validation - Precipitation process Implementation | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-26 14:10 | 0 | 2025-05-26 17:39 | 2025-04-24 15:41 | Customization - Business Logic
User Story | 495923 | Feature Validation - Filter + Dryer + Milling process Implementation | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-26 14:10 | 0 | 2025-05-26 17:40 | 2025-04-24 15:43 | Customization - Business Logic
User Story | 498653 | Feature Validation - Resuspension process Implementation | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-26 14:10 | 0 | 2025-06-12 17:54 | 2025-05-08 10:00 | Customization - Business Logic
User Story | 498654 | Feature Validation - Holding Process Implementation | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-26 14:10 | 0 | 2025-05-26 17:43 | 2025-05-08 10:01 | Customization - Business Logic
User Story | 508873 | Check Weight Operator Cockpit Integration | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-26 16:45 | 2 | 2025-06-26 14:04 | 2025-06-18 16:35 | Modelling & Configuration
User Story | 505598 | Call and adapt if needed the Service for "Confirm Weight" | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-27 11:27 | 3 | 2025-06-26 14:06 | 2025-06-04 16:43 | Customization - Business Logic
User Story | 510419 | Feature Validation - Final Packaging PO release and material creation | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-27 17:04 | 0 | 2025-06-26 20:42 | 2025-06-25 14:29 | Customization - Business Logic
User Story | 509152 | Create Material on PO Release | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-27 18:47 | 2 | 2025-06-26 17:51 | 2025-06-20 12:20 | Sprint Execution
Bug | 510577 | Release error when PO field is null | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-28 14:02 | 2 | 2025-06-26 15:16 | 2025-06-25 17:59 | Customization - Business Logic
User Story | 509120 | Model Change for PO Completion HA-CMC | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-30 12:46 | 0 | 2025-06-27 11:49 | 2025-06-20 09:57 | Modelling & Configuration
User Story | 508869 | Validate TrackIn Sufficient Quantity on the Feeder | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-30 13:26 | 3 | 2025-06-25 10:18 | 2025-06-18 16:29 | Modelling & Configuration
User Story | 508877 | Validate TrackOut Sufficient Quantity on the Feeder | Resolved | DSM-Firmenich\Sprint 07 | 2025-06-30 13:26 | 3 | 2025-06-26 08:20 | 2025-06-18 16:42 | Modelling & Configuration
Bug | 504151 | Tolerances from SAP are miscalculated in MES | Resolved | DSM-Firmenich\Sprint 07 | 2025-07-01 10:59 | 2 | 2025-06-30 14:25 | 2025-05-29 13:53 | Integration - 3rd Party
User Story | 509140 | Automatic Receive on Ship Operation | Resolved | DSM-Firmenich\Sprint 07 | 2025-07-01 11:46 | 3 | 2025-06-27 17:10 | 2025-06-20 11:41 | Sprint Execution
User Story | 508851 | [Modeling] Checklist for sampling confirmation | Resolved | DSM-Firmenich\Sprint 07 | 2025-07-03 14:59 | 1 | 2025-06-23 14:03 | 2025-06-18 16:06 | Modelling & Configuration
User Story | 509216 | Sprint 07 Tax | Resolved | DSM-Firmenich\Sprint 07 | 2025-07-13 20:20 | 0 | 2025-06-30 13:58 | 2025-06-20 15:33 | Sprint Execution
User Story | 509217 | Release Management | Resolved | DSM-Firmenich\Sprint 07 | 2025-07-13 20:20 | 0 | 2025-06-30 13:58 | 2025-06-20 15:40 | Release Management
User Story | 509219 | Sprint 07 Issue Management | Resolved | DSM-Firmenich\Sprint 07 | 2025-07-13 20:20 | 0 | 2025-07-13 20:20 | 2025-06-20 15:42 | Customer Support
User Story | 509235 | Backlog Refinement & Preparation | Resolved | DSM-Firmenich\Sprint 07 | 2025-07-13 20:20 | 0 | 2025-07-13 20:20 | 2025-06-20 16:40 | Modelling & Configuration
User Story | 510326 | [Modelling] Create Protocol for CIP | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-04 16:34 | 1 | 2025-07-04 16:34 | 2025-06-25 11:50 | Customization - Business Logic
User Story | 512713 | [Internal Enhancement] - Apply GetStepMaterials instead of oob service | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-07 19:10 | 0 | 2025-07-07 12:27 | 2025-07-03 15:19 | Customization - GUI Logic
User Story | 504150 | [ENHANCEMENT] Show BOM in the Operator Cockpit | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-08 10:26 | 8 | 2025-07-02 09:59 | 2025-05-29 13:47 | Customization - GUI Logic
User Story | 511927 | [ENHANCEMENT] Standardize Custom Cockpit | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-08 12:29 | 5 | 2025-07-07 08:01 | 2025-07-01 11:38 | Customization - GUI Logic
User Story | 511933 | [ENHANCEMENT] Standardize Custom Cockpit -Rework | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-08 12:29 | 3 | 2025-07-07 08:05 | 2025-07-01 11:46 | Customization - GUI Logic
User Story | 509639 | [Modelling] Create Protocol | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-08 16:53 | 1 | 2025-07-08 16:53 | 2025-06-23 11:51 | Modelling & Configuration
User Story | 509643 | [Modelling] Create Protocol | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-09 16:26 | 1 | 2025-07-09 16:26 | 2025-06-23 12:02 | Modelling & Configuration
User Story | 509244 | [ENHANCEMENT] Master Data Reconciliation | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-11 13:23 | 5 | 2025-07-07 09:14 | 2025-06-20 16:46 | Modelling & Configuration
User Story | 510327 | Implement logic to pass the Protocol state to Dirty automatically | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-11 14:19 | 5 | 2025-07-03 11:02 | 2025-06-25 11:56 | Customization - Business Logic
User Story | 512571 | Implement logic to change ProtocolInstance CIP Attributes by DEE | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-11 14:19 | 5 | 2025-07-04 13:58 | 2025-07-03 11:26 | Customization - Business Logic
User Story | 512169 | [Modelling] Create Notification Template | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-11 15:27 | 1 | 2025-07-08 19:41 | 2025-07-02 11:52 | Modelling & Configuration
User Story | 511993 | [ENHANCEMENT] Weighing PO Model update | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-11 19:09 | 1 | 2025-07-10 21:41 | 2025-07-01 14:47 | Customization - Business Logic
User Story | 509640 | Implement Product Quality Sign-Off Process | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-12 11:31 | 5 | 2025-07-05 11:58 | 2025-06-23 11:58 | Customization - Business Logic
User Story | 510413 | Feature Validation - Sterilize Shipping & Receiving Implementation | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-15 09:27 | 0 | 2025-07-14 23:48 | 2025-06-25 14:25 | Customization - Business Logic
Bug | 515540 | Resuspension Documentation Error | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-15 16:02 | 1 | 2025-07-15 15:43 | 2025-07-15 15:35 | Modelling & Configuration
User Story | 498656 | Feature Validation - Casting Process Implementation | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-17 13:41 | 0 | 2025-06-27 14:04 | 2025-05-08 10:02 | Customization - Business Logic
User Story | 502419 | Feature Validation - Implement Cutting Process | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-17 13:41 | 0 | 2025-06-05 17:01 | 2025-05-22 19:57 | Customization - Business Logic
User Story | 512807 | Feature Validation - CIP process Implementation | Resolved | DSM-Firmenich\Sprint 08 | 2025-07-17 13:41 | 0 | 2025-07-15 09:27 | 2025-07-03 18:48 | Customization - Business Logic
User Story | 505300 | [ENHANCEMENT] Update payload | Resolved | DSM-Firmenich\Sprint 08 | 2025-08-27 13:51 | 5 | 2025-07-30 10:17 | 2025-06-03 18:09 | Integration - 3rd Party
User Story | 512586 | Sprint 08 Tax | Resolved | DSM-Firmenich\Sprint 08 | 2025-12-02 10:01 | 0 | 2025-07-08 14:11 | 2025-07-03 12:06 | Sprint Execution
Bug | 513803 | Mandatory Source Step | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-17 12:26 | 2 | 2025-07-17 12:19 | 2025-07-09 15:20 | Customization - Business Logic
User Story | 509645 | Implement Product Quality Sign-Off Process | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-18 17:19 | 3 | 2025-07-17 10:33 | 2025-06-23 12:04 | Customization - Business Logic
User Story | 510305 | Implement Update Production Orders Process | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-18 18:03 | 3 | 2025-07-08 10:22 | 2025-06-25 11:07 | Customization - Business Logic
User Story | 512173 | Create/Store CustomEntity CustomMaterialConsumptionGoodsIssue | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-21 14:34 | 3 | 2025-07-07 17:33 | 2025-07-02 12:05 | Customization - Business Logic
User Story | 512176 | Create Integration Entry to send Goods Issue | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-22 11:38 | 8 | 2025-07-11 06:53 | 2025-07-02 12:06 | Customization - Business Logic
User Story | 503053 | Feature Validation - Full Pouching process Implementation | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-22 16:49 |  | 2025-07-08 14:26 | 2025-05-26 17:55 | Customization - Business Logic
User Story | 515508 | [Modelling] NCR Material constraints | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-23 22:07 | 1 | 2025-07-23 14:07 | 2025-07-15 13:56 | Modelling & Configuration
User Story | 516092 | Feature Validation - NCR Material constraints | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-23 22:08 |  | 2025-07-23 22:06 | 2025-07-17 09:19 | Customization - Business Logic
User Story | 515448 | Implement Combine Validations | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-24 19:45 | 3 | 2025-07-22 10:22 | 2025-07-15 12:12 | Customization - Business Logic
User Story | 513693 | Create/Store CustomEntity CustomMaterialGoodsReceipt | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-25 07:49 | 3 | 2025-07-22 08:56 | 2025-07-09 11:30 | Customization - Business Logic
User Story | 515449 | Implement Combine Validation at Trackout | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-25 08:49 | 3 | 2025-07-18 10:08 | 2025-07-15 12:13 | Customization - Business Logic
User Story | 516186 | Feature Validation - Quality Alerts Implementation | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-25 11:30 |  | 2025-07-23 22:54 | 2025-07-17 10:40 | Customization - Business Logic
User Story | 513692 | Create Integration Entry to send Goods Receipt | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-25 14:06 | 3 | 2025-07-21 10:25 | 2025-07-09 11:29 | Customization - Business Logic
User Story | 515506 | [Modelling] Quality Alerts Implementation | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-25 14:10 | 1 | 2025-07-23 14:07 | 2025-07-15 13:55 | Migrations & Updates
User Story | 516855 | Meeting with DSM - DataCollection Configuration + other questions | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-25 17:05 | 0 | 2025-07-21 10:05 | 2025-07-18 18:13 | Customer Support
Bug | 518198 | Missing Custom Tables in Documentation | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-28 11:35 | 1 | 2025-07-24 11:48 | 2025-07-24 11:21 | Customization - Business Logic
User Story | 505364 | Feature Validation - Half/Quarter Pouching Implementation - Sleeves | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-28 20:41 |  | 2025-07-08 14:26 | 2025-06-04 09:14 | Customization - Business Logic
User Story | 505366 | Feature Validation - Half/Quarter Pouching Implementation - Pouches | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-28 20:41 |  | 2025-07-08 14:26 | 2025-06-04 09:14 | Customization - Business Logic
User Story | 503057 | Feature Validation - Check-Weight Operator cockpit design and implementation | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-28 20:41 |  | 2025-06-24 16:52 | 2025-05-26 17:57 | Customization - GUI Logic
User Story | 512798 | Feature Validation - Final Product Quality sign-off | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-28 20:42 |  | 2025-07-28 14:01 | 2025-07-03 18:43 | Customization - Business Logic
User Story | 512804 | Feature Validation - Update POs in MES | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-28 20:43 |  | 2025-07-28 14:02 | 2025-07-03 18:47 | Customization - Business Logic
User Story | 513713 | Prevent Dispatch when Resource is not Calibrated | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-29 13:29 | 3 | 2025-07-24 10:06 | 2025-07-09 12:33 | Customization - Business Logic
User Story | 513697 | [Modelling] Create Notification Template (GR) | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-29 19:03 | 1 | 2025-07-29 18:56 | 2025-07-09 11:32 | Modelling & Configuration
User Story | 512801 | Feature Validation - Semi-Finished Quality sign-off | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-29 19:04 |  | 2025-07-28 14:01 | 2025-07-03 18:46 | Customization - Business Logic
User Story | 513696 | Feature Validation - Goods Receipt to SAP | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-29 19:06 |  | 2025-07-29 18:56 | 2025-07-09 11:31 | Customization - Business Logic
User Story | 517190 | Backlog Refinement & Preparation | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-30 04:41 |  | 2025-07-25 16:22 | 2025-07-21 17:27 | Modelling & Configuration
User Story | 516196 | eBR Pre-preparation | Resolved | DSM-Firmenich\Sprint 09 | 2025-07-30 12:00 |  | 2025-07-25 14:27 | 2025-07-17 11:01 | Analytics & BI
User Story | 516277 | Sprint 09 Tax | Resolved | DSM-Firmenich\Sprint 09 | 2025-12-02 10:01 | 0 | 2025-07-23 10:09 | 2025-07-17 14:45 | Sprint Execution
User Story | 517514 | [ENHANCEMENT] BOM Base Qty | Resolved | DSM-Firmenich\Sprint 10 | 2025-07-31 20:07 | 2 | 2025-07-30 11:08 | 2025-07-23 10:00 | Integration - 3rd Party
User Story | 517504 | [ENHANCEMENT] Calculate Sterilize Before Data | Resolved | DSM-Firmenich\Sprint 10 | 2025-08-01 08:40 | 3 | 2025-07-31 14:36 | 2025-07-23 09:24 | Customization - Business Logic
User Story | 513701 | Implement Integration with Blue Mountain | Resolved | DSM-Firmenich\Sprint 10 | 2025-08-01 10:38 | 8 | 2025-07-28 10:19 | 2025-07-09 12:01 | Customization - Business Logic
User Story | 516258 | [ENHANCEMENT] Inherit Expiry Date | Resolved | DSM-Firmenich\Sprint 10 | 2025-08-01 13:56 | 2 | 2025-08-01 13:56 | 2025-07-17 12:56 | Customization - Business Logic
Bug | 518817 | Check weight cockpit not allowing weight value in decimal from the scale | Resolved | DSM-Firmenich\Sprint 10 | 2025-08-04 15:45 | 2 | 2025-07-30 16:07 | 2025-07-28 09:19 | Customization - GUI Logic
User Story | 516639 | [ENHANCEMENT] Add Print Button | Resolved | DSM-Firmenich\Sprint 10 | 2025-08-05 15:24 | 3 | 2025-08-05 10:20 | 2025-07-18 10:51 | Customization - GUI Logic
User Story | 516091 | Feature Validation - Combine Operation Validation | Resolved | DSM-Firmenich\Sprint 10 | 2025-08-06 14:52 |  | 2025-07-30 10:18 | 2025-07-17 09:16 | Customization - Business Logic
User Story | 492264 | Feature Validation - Raw Material Weighing Implementation | Resolved | DSM-Firmenich\Sprint 10 | 2025-08-06 14:55 |  | 2025-07-03 18:41 | 2025-04-10 15:48 | Customization - Business Logic
User Story | 521535 | Feature Validation - [ENHANCEMENT] Calculate Sterilize Before Data | Resolved | DSM-Firmenich\Sprint 10 | 2025-08-07 14:22 |  | 2025-08-05 17:06 | 2025-08-05 17:04 | Customization - Business Logic
User Story | 520694 | Sprint 10 - Master Data Reconciliation | Resolved | DSM-Firmenich\Sprint 10 | 2025-08-08 10:55 |  | 2025-08-08 10:55 | 2025-07-31 09:52 | Modelling & Configuration
User Story | 516636 | [ENHANCEMENT] Add Print Button | Resolved | DSM-Firmenich\Sprint 10 | 2025-08-11 19:40 | 3 | 2025-08-11 16:02 | 2025-07-18 10:44 | Customization - GUI Logic
User Story | 519940 | [ENHANCEMENT] Import Raw Materials - Storage Bins Rules | Resolved | DSM-Firmenich\Sprint 10 | 2025-08-11 19:40 | 8 | 2025-08-04 14:14 | 2025-07-29 16:12 | Integration - 3rd Party
Bug | 519257 | Heat Sealing Losses Reporting | Resolved | DSM-Firmenich\Sprint 10 | 2025-08-13 10:18 | 3 | 2025-08-06 10:18 | 2025-07-28 17:42 | Customization - Business Logic
User Story | 522429 | Feature Validation - GoodsReceipt and GoodsIssue | Resolved | DSM-Firmenich\Sprint 10 | 2025-08-13 13:22 |  | 2025-08-11 18:57 | 2025-08-09 14:05 | Customization - Business Logic
Bug | 523995 | Event missing for the Cutting Driver definition | Resolved | DSM-Firmenich\Sprint 10 | 2025-08-13 17:38 | 1 | 2025-08-13 17:36 | 2025-08-13 16:19 | Integration - Equipment / Connect IoT
User Story | 516089 | Feature Validation - Individual calibration check | Resolved | DSM-Firmenich\Sprint 10 | 2025-08-14 13:22 |  | 2025-07-29 19:36 | 2025-07-17 09:15 | Customization - Business Logic
User Story | 523896 | [ENHANCEMENT] Change Table Column label | Resolved | DSM-Firmenich\Sprint 11 | 2025-08-14 17:47 | 2 | 2025-08-14 11:27 | 2025-08-13 15:18 | Customization - Business Logic
User Story | 492260 | Feature Validation - Import Materials from SAP to MES | Resolved | DSM-Firmenich\Sprint 11 | 2025-08-20 20:49 |  | 2025-07-31 09:58 | 2025-04-10 15:46 | Integration - 3rd Party
Bug | 524001 | Missing IoT Configuration parameters in MES & UG Document | Resolved | DSM-Firmenich\Sprint 11 | 2025-08-21 10:19 | 2 | 2025-08-21 10:19 | 2025-08-13 16:27 | Integration - Equipment / Connect IoT
User Story | 522755 | State models | Resolved | DSM-Firmenich\Sprint 11 | 2025-08-21 12:01 | 5 | 2025-08-14 18:00 | 2025-08-11 16:05 | Integration - Equipment / Connect IoT
Bug | 524414 | Sample Loss Configuration | Resolved | DSM-Firmenich\Sprint 11 | 2025-08-21 14:04 | 2 | 2025-08-21 14:04 | 2025-08-14 14:13 | Customization - Business Logic
Bug | 526598 | Quality Alert Documentation Errors | Resolved | DSM-Firmenich\Sprint 11 | 2025-08-25 12:34 | 1 | 2025-08-25 12:34 | 2025-08-25 12:30 | Customization - Business Logic
User Story | 510409 | Feature Validation - Heat Sealing process Implementation | Resolved | DSM-Firmenich\Sprint 11 | 2025-08-25 14:58 |  | 2025-07-31 09:55 | 2025-06-25 14:22 | Customization - Business Logic
User Story | 524020 | Sprint 11 - Master Data Reconciliation | Resolved | DSM-Firmenich\Sprint 11 | 2025-08-25 16:15 |  | 2025-08-18 17:37 | 2025-08-13 16:50 | Modelling & Configuration
User Story | 492249 | Feature Validation - Push POs from SAP to MES | Resolved | DSM-Firmenich\Sprint 11 | 2025-08-25 20:08 |  | 2025-08-14 09:55 | 2025-04-10 15:44 | Integration - 3rd Party
Bug | 526662 | Incorrect DEE Order of Operations | Resolved | DSM-Firmenich\Sprint 11 | 2025-08-26 17:54 | 3 | 2025-08-25 18:37 | 2025-08-25 17:00 | Integration - Equipment / Connect IoT
User Story | 522759 | HA-CMC Weighing process Labeling | Resolved | DSM-Firmenich\Sprint 11 | 2025-08-26 18:12 | 5 | 2025-08-26 18:12 | 2025-08-11 16:06 | Customization - Business Logic
User Story | 522757 | Raw Material Weighing – Label Printing | Resolved | DSM-Firmenich\Sprint 11 | 2025-08-26 18:17 | 3 | 2025-08-22 15:06 | 2025-08-11 16:05 | Integration - 3rd Party
User Story | 524281 | Feature Validation - State Models Implementation | Resolved | DSM-Firmenich\Sprint 11 | 2025-08-26 18:17 |  | 2025-08-25 11:01 | 2025-08-14 09:57 | Integration - 3rd Party
User Story | 519180 | EBR | Resolved | DSM-Firmenich\Sprint 11 | 2025-11-27 14:50 | 13 | 2025-08-04 08:17 | 2025-07-28 14:44 | Customization - Business Logic
User Story | 524008 | Sprint 11 - Tax | Resolved | DSM-Firmenich\Sprint 11 | 2025-12-02 10:01 |  | 2025-08-22 16:24 | 2025-08-13 16:47 | Sprint Execution
Bug | 526676 | Sleeves Step - Confirm Weight Showing error on last quantity confirm | Resolved | DSM-Firmenich\Sprint 12 | 2025-08-28 18:16 | 5 | 2025-08-25 18:06 | 2025-08-25 18:05 | Customization - GUI Logic
Bug | 526616 | Report GR- Qty Not Matching | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-01 10:12 | 3 | 2025-08-29 10:10 | 2025-08-25 13:00 | Integration - 3rd Party
Bug | 526981 | Casting PO Completion | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-02 17:41 | 3 | 2025-09-02 09:49 | 2025-08-26 10:21 | Customization - Business Logic
User Story | 527017 | Create DEE to validate the Track Out qty against the Produced Qty | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-03 10:29 | 3 | 2025-08-27 17:33 | 2025-08-26 11:12 | Customization - Business Logic
User Story | 523708 | [ENHANCEMENT] Disable IoT Integration for HCL Combine | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-04 10:29 | 2 | 2025-09-03 10:17 | 2025-08-13 11:42 | Customization - Business Logic
User Story | 524386 | [ENHANCEMENT] Hold Reason Labels - HA-CMC Operator Cockpit | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-04 11:04 | 3 | 2025-09-02 10:16 | 2025-08-14 12:51 | Customization - GUI Logic
User Story | 524387 | [ENHANCEMENT] Hold Reason Labels - Check Weight Operator Cockpit | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-04 11:04 | 2 | 2025-09-03 20:57 | 2025-08-14 12:52 | Customization - GUI Logic
User Story | 524388 | [ENHANCEMENT] Hold Reason Labels - Rework Process | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-04 11:04 | 2 | 2025-09-03 20:57 | 2025-08-14 12:52 | Customization - GUI Logic
User Story | 527019 | Create In-Process Labels | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-04 12:41 | 2 | 2025-08-29 10:21 | 2025-08-26 11:17 | Customization - Business Logic
User Story | 516670 | [ENHANCEMENT] Print Heat Sealing bin label | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-04 12:41 | 2 | 2025-08-29 10:21 | 2025-07-18 11:51 | Customization - Business Logic
User Story | 527652 | Mark Feature as resolved | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-04 14:09 | 0 | 2025-09-04 14:09 | 2025-08-27 18:18 | Modelling & Configuration
Bug | 529069 | Ignore Combine Validation for Reference items | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-04 14:17 | 2 | 2025-09-03 19:01 | 2025-09-03 19:00 | Customization - Business Logic
Bug | 528119 | Missing IoT State Model implementations | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-04 19:26 | 3 | 2025-09-01 10:13 | 2025-08-28 18:11 | Integration - Equipment / Connect IoT
User Story | 528064 | Sprint 12 - Release Management | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-05 14:11 |  | 2025-09-05 14:11 | 2025-08-28 15:32 | Release Management
User Story | 527161 | Expiration date based on consumables | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-08 10:07 | 5 | 2025-09-05 11:53 | 2025-08-26 11:33 | Customization - Business Logic
User Story | 527651 | Display Process Instructions Document - User Guide | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-08 14:10 | 1 | 2025-09-04 18:57 | 2025-08-27 18:16 | Modelling & Configuration
User Story | 527653 | Process walkthrough checklist modelling - User Guide | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-08 14:10 | 1 | 2025-09-01 19:49 | 2025-08-27 18:19 | Modelling & Configuration
User Story | 515433 | Expiration date based on Checklist item | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-08 17:28 | 3 | 2025-09-04 19:26 | 2025-07-15 11:38 | Customization - Business Logic
User Story | 527159 | Add checklist item "Expiry Date" to "SF HA-CMC Sign-Off" and "SF Packed Seprafilm Sign-Off" | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-09 21:13 | 1 | 2025-08-28 19:42 | 2025-08-26 11:30 | Modelling & Configuration
User Story | 524484 | [Continuation] Updated EBR requirements | Resolved | DSM-Firmenich\Sprint 12 | 2025-09-10 12:18 | 8 | 2025-08-28 11:11 | 2025-08-14 17:42 | Customization - Business Logic
User Story | 527985 | Sprint 12 - Tax | Resolved | DSM-Firmenich\Sprint 12 | 2025-12-02 10:01 | 0 | 2025-09-09 15:06 | 2025-08-28 14:47 | Sprint Execution
Bug | 529256 | Move Next on Line Storage | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-11 17:26 | 2 | 2025-09-11 10:48 | 2025-09-04 14:30 | Customization - GUI Logic
User Story | 529046 | [ENHANCEMENT] Exclude Co-Products from the Material qty calculation | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-12 16:53 | 2 | 2025-09-12 16:53 | 2025-09-03 17:46 | Customization - Business Logic
User Story | 529374 | Final Packaging Process - Build two printable documents and activate ValidateInstrumentAtTrackIn | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-15 15:48 | 2 | 2025-09-10 12:41 | 2025-09-04 18:32 | Customization - Business Logic
User Story | 528537 | [ENHANCEMENT] Check-In/Out buttons | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-15 18:04 | 2 | 2025-09-15 17:09 | 2025-09-01 16:58 | Customization - GUI Logic
User Story | 530512 | [Continuation] - Enhancement of EBR - Footer and Attachment | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-16 10:22 | 2 | 2025-09-11 10:45 | 2025-09-10 14:20 | Customization - Business Logic
User Story | 528536 | [ENHANCEMENT] Check-In/Out buttons | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-16 11:15 | 2 | 2025-09-16 09:35 | 2025-09-01 16:54 | Customization - GUI Logic
User Story | 528535 | [ENHANCEMENT] Check-In/Out buttons | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-16 16:39 | 3 | 2025-09-16 11:19 | 2025-09-01 16:44 | Customization - GUI Logic
User Story | 524282 | Feature Validation - HA-CMC Weighing process Labeling | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-18 13:54 |  | 2025-09-04 19:02 | 2025-08-14 09:57 | Integration - 3rd Party
User Story | 529052 | [ENHANCEMENT] Update BOM for Unreleased POs | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-18 14:07 | 3 | 2025-09-12 11:21 | 2025-09-03 18:01 | Integration - 3rd Party
User Story | 531109 | Feature Validation - HA-CMC Check-In/Out buttons | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-18 18:51 |  | 2025-09-18 18:40 | 2025-09-12 15:12 | Customization - GUI Logic
User Story | 531113 | Feature Validation - Check weight Cockpit Check-In/Out buttons | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-18 18:51 |  | 2025-09-18 18:40 | 2025-09-12 15:22 | Customization - GUI Logic
User Story | 531115 | Feature Validation - Rework Cockpit - Check-In/Out buttons | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-18 18:51 |  | 2025-09-18 18:40 | 2025-09-12 15:24 | Customization - GUI Logic
User Story | 512867 | [ENHANCEMENT] Error Proof confirm Weight Double Click | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-19 15:11 | 5 |  | 2025-07-04 09:06 | Customization - GUI Logic
User Story | 529377 | Authentication Strategies Investigation | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-19 15:11 |  | 2025-09-04 19:06 | 2025-09-04 19:06 | Sprint Execution
User Story | 532422 | Feature Validation - Error Proof confirm Weight Double Click | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-19 20:11 |  | 2025-09-18 22:08 | 2025-09-18 21:53 | Customization - GUI Logic
User Story | 524283 | Feature Validation - Raw Material Weighing – Label Printing | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-22 10:58 |  | 2025-09-04 19:02 | 2025-08-14 09:57 | Integration - 3rd Party
User Story | 527635 | Feature Validation - Expiration Date Calculation | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-22 10:58 |  | 2025-09-19 18:30 | 2025-08-27 17:51 | Integration - 3rd Party
User Story | 531095 | Feature Validation - Update BOM for Unreleased POs | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-22 17:16 |  | 2025-09-19 21:10 | 2025-09-12 14:44 | Integration - 3rd Party
Bug | 531957 | Missing IoT Driver/Controller | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-23 11:09 | 1 | 2025-09-22 10:28 | 2025-09-17 11:31 | Integration - Equipment / Connect IoT
User Story | 531943 | [ENHANCEMENT] MESReady not resetting on various conditions | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-23 11:10 | 5 | 2025-09-18 14:45 | 2025-09-17 11:10 | Integration - Equipment / Connect IoT
User Story | 533063 | Feature Validation - Sterilize Packaging Implementation - Products & BOM | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-23 16:58 |  | 2025-09-23 16:58 | 2025-09-22 22:03 | Integration - 3rd Party
User Story | 529375 | Terminate POS and BOMS by Timer | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-23 18:24 | 3 | 2025-09-23 14:01 | 2025-09-04 18:33 | Customization - Business Logic
User Story | 531333 | Sprint 13 - Master Data Reconciliation | Resolved | DSM-Firmenich\Sprint 13 | 2025-09-25 19:45 |  | 2025-09-15 14:30 | 2025-09-15 14:29 | Modelling & Configuration
User Story | 530930 | Sprint 13 Tax | Resolved | DSM-Firmenich\Sprint 13 | 2025-12-02 10:01 |  | 2025-12-02 10:01 | 2025-09-11 15:47 | Sprint Execution
User Story | 512881 | [ENHANCEMENT] Weighing PO Management updates | Resolved | DSM-Firmenich\Sprint 14 | 2025-09-30 10:08 | 3 | 2025-09-22 14:09 | 2025-07-04 09:30 | Customization - Business Logic
User Story | 527636 | Feature Validation - Sterilize Packaging Implementation | Resolved | DSM-Firmenich\Sprint 14 | 2025-09-30 14:07 |  | 2025-09-26 14:16 | 2025-08-27 17:51 | Integration - 3rd Party
Bug | 532081 | Allow Combine only for In-Process Materials | Resolved | DSM-Firmenich\Sprint 14 | 2025-09-30 15:21 | 2 | 2025-09-26 14:18 | 2025-09-17 18:22 | Customization - Business Logic
Bug | 532075 | Report GR in different operations | Resolved | DSM-Firmenich\Sprint 14 | 2025-09-30 15:44 | 3 | 2025-09-29 09:55 | 2025-09-17 18:01 | Integration - 3rd Party
Bug | 533036 | Adjust Cockpit tables | Resolved | DSM-Firmenich\Sprint 14 | 2025-09-30 17:01 | 2 | 2025-09-30 12:36 | 2025-09-22 17:50 | Customization - GUI Logic
User Story | 532040 | Feature Validation - Final Packaging Process Implementation | Resolved | DSM-Firmenich\Sprint 14 | 2025-10-01 15:45 |  | 2025-09-26 14:16 | 2025-09-17 16:17 | Integration - 3rd Party
Bug | 535458 | Value is not correctly shown for steps with multiple Resources | Resolved | DSM-Firmenich\Sprint 14 | 2025-10-02 12:11 | 3 | 2025-10-02 08:56 | 2025-10-01 14:57 | Integration - Equipment / Connect IoT
Bug | 535658 | BOM Base Quantity not updated on PO Quantity update | Resolved | DSM-Firmenich\Sprint 14 | 2025-10-02 15:24 | 2 | 2025-10-02 15:24 | 2025-10-02 09:40 | Customization - Business Logic
Bug | 535539 | Attach is allowed with Sign-Off Protocol open | Resolved | DSM-Firmenich\Sprint 14 | 2025-10-02 18:59 | 2 | 2025-10-02 11:57 | 2025-10-01 18:19 | Sprint Execution
User Story | 534648 | [ENHANCEMENT] Remove the Pre-Preparation step | Resolved | DSM-Firmenich\Sprint 14 | 2025-10-03 13:10 | 1 | 2025-10-03 13:10 | 2025-09-26 09:51 | Modelling & Configuration
User Story | 533485 | [ENHANCEMENT] Add "Inspection" step | Resolved | DSM-Firmenich\Sprint 14 | 2025-10-03 15:45 | 1 | 2025-10-01 17:19 | 2025-09-23 16:56 | Modelling & Configuration
User Story | 532045 | Feature Validation - Timer to Terminate POs | Resolved | DSM-Firmenich\Sprint 14 | 2025-10-06 10:19 |  | 2025-09-24 16:06 | 2025-09-17 16:18 | Integration - 3rd Party
User Story | 534362 | [ENHANCEMENT] Operator Cockpit - Show Manage Employees Button | Resolved | DSM-Firmenich\Sprint 14 | 2025-10-06 18:24 | 3 | 2025-10-06 18:09 | 2025-09-25 15:34 | Customization - GUI Logic
User Story | 534364 | [ENHANCEMENT] Check-Weight Cockpit - Show Manage Employees Button | Resolved | DSM-Firmenich\Sprint 14 | 2025-10-06 18:24 | 3 | 2025-10-06 18:09 | 2025-09-25 15:35 | Customization - GUI Logic
User Story | 534372 | [ENHANCEMENT] Rework Cockpit - Show Manage Employees Button | Resolved | DSM-Firmenich\Sprint 14 | 2025-10-06 18:24 | 3 | 2025-10-06 18:09 | 2025-09-25 15:41 | Customization - GUI Logic
Bug | 535456 | Only reset MESReady Tag on the final Track-Out | Resolved | DSM-Firmenich\Sprint 14 | 2025-10-07 10:18 | 3 | 2025-10-02 18:59 | 2025-10-01 14:54 | Integration - Equipment / Connect IoT
User Story | 533724 | [ENHANCEMENT] Data Collection IoT Updates for Casting | Resolved | DSM-Firmenich\Sprint 14 | 2025-10-07 10:18 | 3 | 2025-09-30 15:21 | 2025-09-24 10:39 | Integration - Equipment / Connect IoT
User Story | 534090 | [ENHANCEMENT] Data Collection IoT Updates for Cutting | Resolved | DSM-Firmenich\Sprint 14 | 2025-10-07 10:18 | 3 | 2025-10-02 16:09 | 2025-09-25 09:10 | Integration - Equipment / Connect IoT
User Story | 534650 | [ENHANCEMENT] Remove Pre-Preparation logic | Resolved | DSM-Firmenich\Sprint 14 | 2025-10-08 10:17 | 2 | 2025-10-07 10:13 | 2025-09-26 09:58 | Customization - Business Logic
User Story | 534849 | Sprint 14 Tax | Resolved | DSM-Firmenich\Sprint 14 | 2025-12-02 10:01 |  | 2025-10-07 15:28 | 2025-09-26 17:59 | Sprint Execution
User Story | 532189 | [ENHANCEMENT] Use Casting PO qty directly | Resolved | DSM-Firmenich\Sprint 15 | 2025-10-10 17:58 | 3 | 2025-10-07 12:25 | 2025-09-18 10:59 | Customization - Business Logic
User Story | 534344 | Feature Validation - Enhancement - Weighing PO Management updates | Resolved | DSM-Firmenich\Sprint 15 | 2025-10-13 14:01 |  | 2025-10-13 14:00 | 2025-09-25 15:21 | Integration - 3rd Party
User Story | 532209 | [ENHANCEMENT] Remove parts counter automatic Loss | Resolved | DSM-Firmenich\Sprint 15 | 2025-10-13 19:50 | 2 | 2025-10-09 10:21 | 2025-09-18 11:37 | Customization - Business Logic
Bug | 537823 | MES tag reset not occuring | Resolved | DSM-Firmenich\Sprint 15 | 2025-10-14 15:20 | 2 | 2025-10-14 10:38 | 2025-10-14 10:26 | Integration - Equipment / Connect IoT
Bug | 529065 | Timezone Conversion Errors | Resolved | DSM-Firmenich\Sprint 15 | 2025-10-16 10:59 | 5 | 2025-10-02 15:28 | 2025-09-03 18:39 | Customization - Business Logic
Bug | 537197 | EBR Current Issues | Resolved | DSM-Firmenich\Sprint 15 | 2025-10-21 10:20 | 3 | 2025-10-14 03:08 | 2025-10-09 11:57 | Customization - Business Logic
Bug | 538491 | Update BOMs with only one component | Resolved | DSM-Firmenich\Sprint 15 | 2025-10-21 10:29 | 1 | 2025-10-20 09:36 | 2025-10-16 09:41 | Integration - 3rd Party
User Story | 536216 | [ENHANCEMENT] Consider Co-Products for Virtual Material qty | Resolved | DSM-Firmenich\Sprint 15 | 2025-10-21 17:49 | 2 | 2025-10-21 17:49 | 2025-10-06 16:57 | Customization - Business Logic
User Story | 534325 | Feature Validation - Enhancement Use Casting PO qty directly | Resolved | DSM-Firmenich\Sprint 15 | 2025-10-22 15:09 |  | 2025-10-21 15:45 | 2025-09-25 15:13 | Integration - 3rd Party
User Story | 532232 | [ENHANCEMENT] Update cutting process | Resolved | DSM-Firmenich\Sprint 15 | 2025-10-27 10:52 | 5 | 2025-10-13 10:11 | 2025-09-18 12:37 | Customization - Business Logic
User Story | 537302 | Sprint 15 Tax | Resolved | DSM-Firmenich\Sprint 15 | 2025-12-02 10:01 |  | 2025-12-02 10:01 | 2025-10-09 17:29 | Sprint Execution
User Story | 540487 | Sprint 16 - Master Data Reconciliation | Resolved | DSM-Firmenich\Sprint 16 | 2025-10-24 11:43 |  | 2025-10-24 11:43 | 2025-10-23 15:26 | Modelling & Configuration
User Story | 534326 | Feature Validation - Enhancement - Remove parts counter automatic Loss | Resolved | DSM-Firmenich\Sprint 16 | 2025-10-28 19:18 |  | 2025-10-21 15:46 | 2025-09-25 15:13 | Integration - 3rd Party
User Story | 533713 | Master Batch Record Report Implementation | Resolved | DSM-Firmenich\Sprint 16 | 2025-10-29 15:51 | 8 | 2025-10-09 12:18 | 2025-09-24 10:22 | Customization - Business Logic
User Story | 534327 | Feature Validation - Enhancement - Update cutting process + Virtual Material | Resolved | DSM-Firmenich\Sprint 16 | 2025-10-29 16:18 |  | 2025-10-28 11:30 | 2025-09-25 15:13 | Integration - 3rd Party
User Story | 529045 | [ENHANCEMENT] Report GR for co-products | Resolved | DSM-Firmenich\Sprint 16 | 2025-10-31 18:49 | 1 | 2025-10-31 18:49 | 2025-09-03 17:34 | Integration - 3rd Party
User Story | 531118 | Feature Validation - Enhancement - Report GR for co-products | Resolved | DSM-Firmenich\Sprint 16 | 2025-10-31 18:51 |  | 2025-10-31 18:51 | 2025-09-12 15:28 | Integration - 3rd Party
Bug | 541454 | Aliquot PO Batch is Wrong | Resolved | DSM-Firmenich\Sprint 16 | 2025-11-04 09:51 | 2 | 2025-10-31 10:19 | 2025-10-28 11:01 | Customization - Business Logic
User Story | 541774 | IoT Connection Master Data Verification | Resolved | DSM-Firmenich\Sprint 16 | 2025-11-04 10:17 |  | 2025-11-04 02:30 | 2025-10-29 13:42 | Integration - Equipment / Connect IoT
User Story | 533714 | Operation confirmation to SAP (phase confirmation) | Resolved | DSM-Firmenich\Sprint 16 | 2025-11-05 16:40 | 8 | 2025-10-22 09:51 | 2025-09-24 10:22 | Integration - 3rd Party
Bug | 544135 | GR & GI at the same step is not possible | Resolved | DSM-Firmenich\Sprint 16 | 2025-11-12 10:44 | 2 | 2025-11-07 12:04 | 2025-11-06 16:16 | Customization - Business Logic
User Story | 535195 | Operation confirmation to SAP - perform needed calculations | Resolved | DSM-Firmenich\Sprint 16 | 2025-11-12 11:37 | 5 | 2025-10-24 09:01 | 2025-09-30 11:51 | Integration - 3rd Party
Bug | 541775 | Expiration Date changes for Final Packaging | Resolved | DSM-Firmenich\Sprint 16 | 2025-11-12 11:52 | 3 | 2025-11-11 13:24 | 2025-10-29 13:42 | Customization - Business Logic
User Story | 534303 | Feature Validation - Master Batch Record Report Implementation | Resolved | DSM-Firmenich\Sprint 16 | 2025-11-12 16:59 |  | 2025-11-03 10:33 | 2025-09-25 15:04 | Integration - 3rd Party
Bug | 541897 | Produced Qty not Reset | Resolved | DSM-Firmenich\Sprint 16 | 2025-11-13 14:57 | 2 | 2025-11-13 14:02 | 2025-10-29 16:24 | Customization - Business Logic
Bug | 542504 | Bullet Points in EBR Checklists & Repeated Data Collections & Checklist's embedded DCs, Signatures and Order | Resolved | DSM-Firmenich\Sprint 16 | 2025-11-14 14:47 | 5 | 2025-11-11 02:17 | 2025-11-03 09:27 | Customization - Business Logic
User Story | 527637 | Feature Validation - EBR Design and Implementation | Resolved | DSM-Firmenich\Sprint 16 | 2025-11-14 16:40 |  | 2025-09-10 14:04 | 2025-08-27 17:51 | Integration - 3rd Party
Bug | 537514 | W&D button not visible + not showing Track out button After W&D Completion | Resolved | DSM-Firmenich\Sprint 16 | 2025-11-17 20:01 | 3 | 2025-11-13 15:29 | 2025-10-10 19:02 | Customization - GUI Logic
User Story | 534312 | Feature Validation - Operation confirmation to SAP (phase confirmation) | Resolved | DSM-Firmenich\Sprint 16 | 2025-11-19 18:47 |  | 2025-11-04 18:31 | 2025-09-25 15:08 | Integration - 3rd Party
User Story | 540484 | Sprint 16 Tax | Resolved | DSM-Firmenich\Sprint 16 | 2025-12-02 10:01 |  | 2025-10-31 08:25 | 2025-10-23 15:25 | Sprint Execution
User Story | 548311 | Sprint 17 Tax | Resolved | DSM-Firmenich\Sprint 17 | 2026-02-03 10:53 |  | 2026-02-03 10:53 | 2025-11-26 10:18 | Sprint Execution
User Story | 555892 | Sprint 17 - Release Management | Resolved | DSM-Firmenich\Sprint 17 | 2026-05-18 09:00 |  | 2026-01-13 13:09 | 2026-01-13 13:09 | Release Management
Bug | 548295 | ResolveFromTable option is not present in the configuration | Resolved | DSM-Firmenich\Sprint 18 | 2026-01-21 08:51 | 1 | 2026-01-21 08:50 | 2025-11-26 10:10 | Customization - Business Logic
Bug | 549855 | Operation Confirmation not sent to SAP | Resolved | DSM-Firmenich\Sprint 18 | 2026-01-21 08:51 | 1 | 2026-01-21 08:50 | 2025-12-03 14:26 | Customization - Business Logic
Bug | 550445 | ConfirmationActivity5 field not sent as NULL to SAP | Resolved | DSM-Firmenich\Sprint 18 | 2026-01-21 08:51 | 1 | 2026-01-19 08:47 | 2025-12-09 10:39 | Customization - Business Logic
Bug | 550681 | Final Confirmation for Aliquot | Resolved | DSM-Firmenich\Sprint 18 | 2026-01-21 08:51 | 2 | 2026-01-19 08:52 | 2025-12-10 11:44 | Customization - Business Logic
Bug | 552603 | Failed Import Material Job Wrongly processed again | Resolved | DSM-Firmenich\Sprint 18 | 2026-01-27 14:17 | 1 | 2026-01-22 11:44 | 2025-12-18 16:46 | Integration - 3rd Party
User Story | 535777 | [ENHANCEMENT] Introduce Planner Comment | Resolved | DSM-Firmenich\Sprint 18 | 2026-01-27 16:46 | 3 | 2026-01-27 08:54 | 2025-10-02 17:17 | Integration - 3rd Party
User Story | 557477 | Feature Validation - Bug | Resolved | DSM-Firmenich\Sprint 18 | 2026-01-28 11:09 |  | 2026-01-28 11:09 | 2026-01-19 16:24 | Integration - 3rd Party
Bug | 551262 | GR API call - Date and Time mismatch between Material and API structure sent to SAP | Resolved | DSM-Firmenich\Sprint 18 | 2026-01-28 12:59 | 3 | 2026-01-21 06:42 | 2025-12-12 09:50 | Integration - 3rd Party
Bug | 554495 | DEEs not mentioned in the documentation | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-02 09:42 | 2 | 2026-01-30 15:29 | 2026-01-06 16:10 | Customization - Business Logic
User Story | 557465 | Feature Validation - Enhancement | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-02 11:39 |  | 2026-02-02 11:39 | 2026-01-19 16:13 | Integration - 3rd Party
User Story | 557466 | Feature Validation - Enhancement | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-02 11:52 |  | 2026-02-02 11:52 | 2026-01-19 16:14 | Integration - 3rd Party
User Story | 557468 | Feature Validation - Enhancement | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-02 11:53 |  | 2026-02-02 11:53 | 2026-01-19 16:14 | Integration - 3rd Party
User Story | 557461 | Feature Validation - Enhancement | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-02 12:22 |  | 2026-02-02 12:22 | 2026-01-19 16:12 | Integration - 3rd Party
User Story | 557478 | Feature Validation - Bug | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-02 12:36 |  | 2026-02-02 12:36 | 2026-01-19 16:25 | Integration - 3rd Party
Bug | 548231 | Tables Showing incorrectly - EBR + Units | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-02 14:43 | 3 | 2026-01-23 08:28 | 2025-11-26 09:27 | Customization - Business Logic
User Story | 549661 | [ENHANCEMENT] Show RecipeGroup and Planner Comment in EBR Header; Ignore images; Add Date | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-02 14:43 | 5 | 2026-02-02 09:25 | 2025-12-03 09:19 | Customization - Business Logic
User Story | 535876 | [ENHANCEMENT] Show Planner Comment + Recipe Revision | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-02 14:47 | 5 | 2026-01-29 10:06 | 2025-10-03 11:37 | Customization - GUI Logic
User Story | 535878 | [ENHANCEMENT] Show Planner Comment + Recipe Revision | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-03 09:43 | 3 | 2026-01-30 15:49 | 2025-10-03 11:39 | Customization - GUI Logic
User Story | 535877 | [ENHANCEMENT] Show Planner Comment + Recipe Revision | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-03 09:43 | 3 | 2026-01-30 15:49 | 2025-10-03 11:39 | Customization - GUI Logic
User Story | 554810 | [ENHANCEMENT] API call sequencing | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-03 09:43 | 5 | 2026-01-30 15:49 | 2026-01-07 16:15 | Integration - 3rd Party
User Story | 557469 | Feature Validation - Enhancement + Bug | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-03 11:23 |  | 2026-01-28 11:12 | 2026-01-19 16:15 | Integration - 3rd Party
Bug | 548229 | Tables Showing incorrectly - MBR | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-03 11:52 | 5 | 2026-01-27 09:20 | 2025-11-26 09:25 | Customization - Business Logic
Bug | 548464 | Embedded DC Parameters are not shown in MBR | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-03 11:52 | 3 | 2026-02-03 09:36 | 2025-11-26 15:13 | Customization - Business Logic
User Story | 536357 | Delete CustomEntities (GI/GR/OC) records when PO is terminated | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-03 12:01 |  | 2026-01-27 16:25 | 2025-10-07 08:55 | Customization - Business Logic
User Story | 557475 | Feature Validation - Bug | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-03 17:33 |  | 2026-02-03 17:33 | 2026-01-19 16:23 | Integration - 3rd Party
User Story | 557467 | Feature Validation - Enhancement + Bug | Resolved | DSM-Firmenich\Sprint 18 | 2026-02-04 12:58 |  | 2026-02-04 11:50 | 2026-01-19 16:14 | Integration - 3rd Party
User Story | 557325 | Sprint 18 Tax | Resolved | DSM-Firmenich\Sprint 18 | 2026-05-18 08:59 |  | 2026-05-18 08:59 | 2026-01-19 09:43 | Sprint Execution
User Story | 557328 | Sprint 18 - Client Meetings/Support | Resolved | DSM-Firmenich\Sprint 18 | 2026-05-18 09:00 |  | 2026-05-18 09:00 | 2026-01-19 09:44 | Customer Support
User Story | 557330 | Sprint 18 - Issue Management | Resolved | DSM-Firmenich\Sprint 18 | 2026-05-18 09:00 |  | 2026-05-18 09:00 | 2026-01-19 09:45 | Customer Support
User Story | 557334 | Sprint 18 - Backlog Refinement & Preparation | Resolved | DSM-Firmenich\Sprint 18 | 2026-05-18 09:00 |  | 2026-05-18 09:00 | 2026-01-19 09:46 | Modelling & Configuration
User Story | 557336 | Sprint 18 - Team Support/Meetings | Resolved | DSM-Firmenich\Sprint 18 | 2026-05-18 09:00 |  | 2026-05-18 09:00 | 2026-01-19 09:47 | Sprint Execution
User Story | 557337 | Sprint 18 - Release Management | Resolved | DSM-Firmenich\Sprint 18 | 2026-05-18 09:00 |  | 2026-05-18 09:00 | 2026-01-19 09:47 | Release Management
User Story | 561166 | Sprint 19 Tax | Resolved | DSM-Firmenich\Sprint 19 | 2026-04-23 09:55 |  | 2026-04-23 09:55 | 2026-02-06 10:58 | Sprint Execution
User Story | 561168 | Sprint 19 - Client Meetings/Support | Resolved | DSM-Firmenich\Sprint 19 | 2026-04-23 09:55 |  | 2026-04-23 09:55 | 2026-02-06 10:59 | Customer Support
User Story | 561171 | Sprint 19 - Backlog Refinement & Preparation | Resolved | DSM-Firmenich\Sprint 19 | 2026-04-23 09:55 |  | 2026-04-23 09:55 | 2026-02-06 11:04 | Modelling & Configuration
User Story | 562110 | Sprint 19 - Issue Management | Resolved | DSM-Firmenich\Sprint 19 | 2026-04-23 09:55 |  | 2026-04-23 09:55 | 2026-02-09 11:21 | Customer Support
User Story | 574996 | Sprint 20 - Issues Management | Resolved | DSM-Firmenich\Sprint 20 | 2026-05-07 09:21 |  | 2026-05-07 09:21 | 2026-04-23 09:58 | Customer Support
User Story | 574998 | Sprint 20 - Backlog Management & Preparation | Resolved | DSM-Firmenich\Sprint 20 | 2026-05-07 09:22 |  | 2026-05-07 09:22 | 2026-04-23 09:59 | Modelling & Configuration
User Story | 574992 | Sprint 20 Tax | Resolved | DSM-Firmenich\Sprint 20 | 2026-05-19 15:22 |  | 2026-05-07 09:21 | 2026-04-23 09:56 | Sprint Execution
User Story | 577079 | [Kaizen] :: Give context of the project to remaining members of the team | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-18 11:31 |  | 2026-05-18 11:31 | 2026-05-06 15:43 | Sprint Execution
User Story | 518630 | Install Medical Template | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-18 12:43 | 5 | 2026-05-18 12:43 | 2025-07-25 13:34 | Customer Installations
User Story | 538119 | Install Version 11.2.6 | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-18 12:43 | 13 | 2026-04-24 17:57 | 2025-10-15 09:29 | Customer Installations
Bug | 562375 | Managing Payload Q Status | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-18 12:45 | 3 | 2026-04-29 13:36 | 2026-02-10 10:48 | Integration - 3rd Party
Bug | 562991 | Expiration Date Not Updated | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-18 12:45 | 3 | 2026-04-30 14:50 | 2026-02-12 10:30 | Integration - 3rd Party
Bug | 563791 | Failed Import Job when Material is Terminated | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-18 12:45 | 5 | 2026-04-30 15:11 | 2026-02-19 10:44 | Integration - 3rd Party
Bug | 564781 | Protocol Instance creation incorrectly blocked | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-18 12:59 | 3 | 2026-05-06 11:40 | 2026-02-24 17:37 | Customization - Business Logic
Bug | 562898 | Allow GR and GI to be sent on MoveNext | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-18 13:16 | 3 | 2026-05-06 16:44 | 2026-02-11 17:07 | Integration - 3rd Party
User Story | 558173 | [ENHANCEMENT] Flexible flow/step for Material creation | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-18 13:33 | 3 | 2026-05-08 08:38 | 2026-01-22 15:45 | Customization - Business Logic
Bug | 562127 | Feature for access management is missing | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-18 14:00 | 2 | 2026-04-27 19:47 | 2026-02-09 12:10 | Customization - Business Logic
User Story | 558408 | [ENHANCEMENT] Adapt logic for manual mode | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-18 15:11 | 5 | 2026-05-11 18:02 | 2026-01-23 15:50 | Customization - Business Logic
User Story | 559990 | Line Clearance User Guide | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-18 15:11 | 2 | 2026-05-15 17:52 | 2026-01-29 14:08 | Modelling & Configuration
User Story | 577167 | Sprint 21 Tax | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-21 14:47 |  | 2026-05-21 14:47 | 2026-05-07 09:17 | Sprint Execution
User Story | 577170 | Sprint 21 - Cliente Meetings/Support | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-25 09:17 |  | 2026-05-25 09:17 | 2026-05-07 09:18 | Customer Support
User Story | 577172 | Sprint 21 - Issues Management | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-25 09:17 |  | 2026-05-25 09:17 | 2026-05-07 09:18 | Customer Support
User Story | 577175 | Sprint 21 - Backlog Management & Preparation | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-25 09:17 |  | 2026-05-25 09:17 | 2026-05-07 09:19 | Modelling & Configuration
User Story | 577190 | Sprint 21 - Release Management | Resolved | DSM-Firmenich\Sprint 21 | 2026-05-25 09:17 |  | 2026-05-19 08:08 | 2026-05-07 10:38 | Release Management
User Story | 577243 | [ENHANCEMENT] Final Confirmation on PO Closure | Resolved | DSM-Firmenich\Sprint 22 | 2026-05-28 12:22 | 8 | 2026-05-21 15:36 | 2026-05-07 16:59 | Integration - 3rd Party
User Story | 573777 | [ENHANCEMENT] Change Setup and Labor time calculation | Resolved | DSM-Firmenich\Sprint 22 | 2026-05-28 16:21 | 8 | 2026-05-22 07:46 | 2026-04-17 15:59 | Customization - Business Logic
User Story | 579208 | [ENHANCEMENT] Change SAP Mapping table | Resolved | DSM-Firmenich\Sprint 22 | 2026-05-28 18:43 | 3 | 2026-05-26 08:19 | 2026-05-20 11:35 | Customization - Business Logic
User Story | 570924 | [ENHANCEMENT] Add ERP Dates as String | Resolved | DSM-Firmenich\Sprint 22 | 2026-06-02 09:36 | 3 | 2026-06-01 23:45 | 2026-03-26 18:39 | Integration - 3rd Party
User Story | 579449 | Sprint 22 - Release Management | Resolved | DSM-Firmenich\Sprint 22 | 2026-06-02 12:00 |  | 2026-06-02 09:18 | 2026-05-21 09:32 | Release Management
User Story | 581720 | Sprint 23 - Release Management | Resolved | DSM-Firmenich\Sprint 23 | 2026-06-15 17:27 |  | 2026-06-15 17:27 | 2026-06-05 11:02 | Release Management
User Story | 562436 | [ENHANCEMENT] Improve EBR - Part I - Generic, Headers and Batch Details | Resolved | DSM-Firmenich\Sprint 23 | 2026-06-17 16:56 | 13 | 2026-06-09 08:34 | 2026-02-10 13:08 | Customization - Business Logic
Bug | 581548 | Combine with Partial Track-Outs | Resolved | DSM-Firmenich\Sprint 24 | 2026-06-24 13:41 | 5 | 2026-06-24 09:14 | 2026-06-03 16:49 | Customization - Business Logic
Bug | 582674 | Manual Mode creating unexpected Materials | Resolved | DSM-Firmenich\Sprint 24 | 2026-06-26 05:22 | 3 | 2026-06-22 09:14 | 2026-06-15 11:09 | Customization - Business Logic